## Proposed Product Backlog
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User | <As a> user <I want to> become a vip <So that> I can access vip feature | 1 | <As a> user, <I want to> pay to become a vip <so that> I can access vip features
|  | 2 | <As a> user, <I want to> use my vip membership <so that> I can get a flat discount rate
|  | 3 | <As a> user, <I want to> access special deals <so that> I can save money
| <As a> user <I want to> have a wishlist <so that> I can save items for a later date | 4 | <As a> User, <I want to> add an item to my wishlist <so that> I can consider the purchase
|  | 5 | <As a> User, <I want to> remove an item from my wishlish <so that> I know I don't want it anymore
|  | 6 | <As a> user, <I want to> add a wishlish item to my cart <so that> I can actually purchase the item
| <As a> user <I want to> have the ability to comment/review a product <so that> I can let others know about products I have bought. | 7 | <As a> user, <I want to> leave a comment <so that> I can review the product
|  | 8 | <As a> user, <I want to> delete my comment <so that> the comment is no longer viewable
|  | 9 | <As a> user, <I want to> edit my comment <so that> the comment reflects my current thoughts or fix spelling errors
|  | 10 | <As a> user, <I want to> filter the items <so that> I can manage what I see
|  | 11 | <As > user, <I wanto to> have a checkout confirmation page <so that> I can make sure my information is right.
|  | 12 | <As a> user, <I want to> products to be displayed through pages <So that> the store looks nice and neat
| <As an> administrator, <I want to> manage all user accounts <so that> I can edit and monitor user accounts for administrative purposes | 13 | <As an> admin, <I want to> show users in a list <so that> I can easily access them
Admin |  | 14 | <As an> admin, <I want to> disable/enable a user <so that> they are no longer able to shop at the store
|  | 15 | <As an> admin <I want to> delete a user <so that> I can maintain a good online community
|  | 16 | <As an> admin <I want to> delete comments <so that> I can maintain a good userbase
|  | 17 | <As an> admin <I want to> remove vip status <so that> I can revoke priviledge from users for breaking rules
| <As an> admin, <I want to> manage products <so that> I can add,edit remove for administrative purposes | 18 | <As an> admin, <I want to> add a product <so that> users can purchase or comment
|  | 19 | <as an> admin, <I want to> remove a product <so that> users can no longer purchase the item.
|  | 20 | <As an> admin, <I want to> edit products <so that> a product reflects the current price, description, and name

## Sprint1
Sprint Backlog: Sprint 1
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User
|  | 1 | <As > user, <I wanto to> have a checkout confirmation page <so that> I can make sure my information is right.
admin | <As an> admin, <I want to> manage products <so that> I can add,edit remove for administrative purposes | 2 | <As an> admin, <I want to> add a product <so that> users can purchase or comment
|  | 3 | <as an> admin, <I want to> remove a product <so that> users can no longer purchase the item.
|  | 4 | <As an> admin, <I want to> edit products <so that> a product reflects the current price, description, and name
| <As an> administrator, <I want to> manage all user accounts <so that> I can edit and monitor user accounts for administrative purposes | 5 | <As an> admin, <I want to> show users in a list <so that> I can easily access them
|  | 6 | <As an> admin, <I want to> disable/enable a user <so that> they are no longer able to shop at the store
|  | 7 | <As an> admin <I want to> delete a user <so that> I can maintain a good online community
Each child user story must have all of 3 clauses too: <As a> … <I want to> … <so that>
You are allowed to introduce a new EPIC that is not in the proposed Product Backlog. In "Notes" column, remark it as a new EPIC. However, do not edit the original Product Backlog.
Some of the epics may be already small enough so that you do not have to split it into multiple child user stories

## Sprint1 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | After hitting the <check out> button the user is directed to a confirmation page | Jason | Jason | Jason | pass
| The confirmation page holds the correct information from the purchase | Jason | Jason | Jason | pass
| The user can cancel the order if it is incorrect by clicking the <cancel> button | Jason | Jason | Jason | pass
| the users shipping will be presented | Jason | Jason | Jason | pass
| The user can confirm the order by clicking the <confirm> button | Jason | Jason | Jason | pass
2 | On the admin product page a <add product> button appears | Jason | Jason | Jason | pass
| When clicking the <add product> button a modal form pops up | Jason | Jason | Jason | pass
| The modal form has spaces to enter | Jason | Jason | Jason | pass
| The new product is added to firebase storage once created | Jason | Jason | Jason | pass
| Once created the new product shows up in the product catalog | Jason | Jason | Jason | pass
3 | On the product card in the catalog there is a <delete> button | Jason | Jason | Jason | pass
| Once the <delete> button is clicked the admin is asked if they are sure | Jason | Jason | Jason | pass
| When the admin confirms the product is removed from the list and firebase storage | Jason | Jason | Jason | pass
4 | On the product card in the catalog there is an <edit> button | Jason | Jason | Jason | pass
| The admin can click the <edit> button and a modal form appears | Jason | Jason | Jason | pass
| The admin can edit any individual attribute of the product | Jason | Jason | Jason | pass
| The product's information is updated inside firebase storage | Jason | Jason | Jason | pass
| The product's information Is updated in the catalog list | Jason | Jason | Jason | pass
5 | Admin page shows a list of users | Jason | Jason | Jason | pass
| The list of users are displayed using bootstrap cards | Jason | Jason | Jason | pass
| Each user card has a delete button | Jason | Jason | Jason | pass
| Each use card has a toggle active button | Jason | Jason | Jason | pass
6 | Each user card has a toggle active button | Jason | Jason | Jason | pass
| Upon pressing toggle the users account status changes from active to disable and reverse | Jason | Jason | Jason | pass
| The card updates with current status of account after each button press | Jason | Jason | Jason | pass
7 | Each user card has a delete button | Jason | Jason | Jason | pass
| When pressing <delete> the user is deleted from the firebase database | Jason | Jason | Jason | pass
| After the user is deleted the user card will be removed from view | Jason | Jason | Jason | pass

## Sprint2
Sprint Backlog: Sprint 2
Category | EPICs (User Stories) | ID | Child User Stories | Assigned To | Status | Notes
User | <As a> user <I want to> have the ability to comment/review a product <so that> I can let others know about products I have bought. | 1 | <As a> user, <I want to> have a way to view comments/reviews
|  | 2 | <As a> user, <I want to> leave a comment <so that> I can review the product
|  | 3 | <As a> user, <I want to> delete my comment <so that> the comment is no longer viewable
|  | 4 | <As a> user, <I want to> edit my comment <so that> the comment reflects my current thoughts or fix spelling errors
admin |  | 5 | <As an> admin <I want to> delete comments <so that> I can maintain a good userbase

## Sprint2 Acceptance
Child User Story ID | Acceptance Criteria | created by (member) | verified by (test engineer) | tested by (test engineer) | Result | Note
1 | Guest can view comments before signing in | Jason | Jason | Jason | pass
| When viewing a product as a user there is a comment button | Jason | Jason | Jason | pass
| when clicking the comment button the user is redirected to the comment page | Jason | Jason | Jason | pass
| On the comment page there is a place comment button | Jason | Jason | Jason | pass
2 | On the comment display form there is a new comment button | Jason | Jason | Jason | pass
| When clicking the new comment button the user is prompted for their comment | Jason | Jason | Jason | pass
| The comment is uploaded and stored in firebase once submited | Jason | Jason | Jason | pass
3 | On the comment display form a delete button appears on the current users comments only | Jason | Jason | Jason | pass
| When deleting the comment the user is asked to confirm | Jason | Jason | Jason | pass
| Once deleted the comment is removed from the comment list | Jason | Jason | Jason | pass
| The comment is removed from firebase storage | Jason | Jason | Jason | pass
4 | On the comment display form there is an edit comment button on the current users comments only | Jason | Jason | Jason | pass
| When edit comment button is clicked the user is promted for input | Jason | Jason | Jason | pass
| When editting the comment is changed on the list | Jason | Jason | Jason | pass
| The firebase storage reflects the edit changes | Jason | Jason | Jason | pass
5 | When signed in as an admin the delete button appears correctly | Jason | Jason | Jason | pass
| The admin will be prompted to confirm before deleting | Jason | Jason | Jason | pass
| The comment will be removed from the firebase storage | Jason | Jason | Jason | pass

## Finalized Product Backlog
ALL "Completed" Child User Stories Based on the Submitted Program.
Category | Child User Stories | Implemented by | Notes